1st December 2021

LHL006/TC

Planning Portal Ref:

PP-10399681

FAO: Mr Edward Snook

Swindon Borough Council

Planning Department

Wat Tyler House

Beckhampton Street

Swindon

SN1 2JH

Dear Edward Snook,

RE: Section 96A of the Town and Country Planning Act 1990 (as amended)

LAND NORTH OF A420, EASTERN VILLAGES: NON-MATERIAL AMENDMENT (‘NMA’) TO VARY CONDITIONS 9, 27, 41, 47, 49 and 61 OF EXTANT OUTLINE PERMISSION S/OUT/13/1555

We are pleased to submit this application on behalf of our client, Hallam/Hannick/Taylor Wimpey (HHT), for a Non-Material Amendment (‘NMA’) to vary conditions 9, 27, 41, 47, 49 and 61 of the outline permission (ref. S/OUT/13/1555) relating to Land north of A420, Eastern Villages Swindon.  This permission was granted by the Council on 11th August 2021.

This application is submitted under the provisions of Section 96a of the Town and Country Planning Act 1990 (as amended) (‘the Act’). Under Section 96a of the Act, NMA applications have the power to amend an existing permission (including the removal, alteration, or addition of conditions), and we have discussed that this is the appropriate mechanism through which to seek the non-material amendments sought in an expedient timeframe to support the wider implementation programme.

BACKGROUND

With HHT focus on implementation activities to include construction strategy and programme, the team have been reviewing the outline planning permission to scope the material requirements to support commencement on site.

A consideration of the timing of the outline conditions, together with the construction programme and construction access strategy has resulted in the need to seek variation to a limited number of conditions to support the construction programme and an early start on site. The scope of the changes sought have been discussed with you prior to the submission of this formal application, through which you have indicated your broad agreement that the proposed rewording is appropriate and necessary.

The amended wording sought is presented below as track changes, together with the rationale to explain the reasons for the variation:

CONDITION 9 – CHARACTER AREA DESIGN CODE

Proposed Wording:

A Design Code relating to each Character Area as defined in the Strategic Design Code, shall be submitted to and be approved in writing by the Local Planning Authority prior to the submission of the first reserved matters application (with the exception of reserved matters applications solely for strategic highway infrastructure) for development parcels within that Character Area. Each Design Code shall be in accordance with the Strategic Design Code approved pursuant to condition 8 above and shall include detailed guidance for that specific Character Area in respect of:

a) The overall vision and character of the character area, and mix of uses;

b) How the character and identity of the development parcel will be established and strengthened through consideration of the public realm, streets, green infrastructure, retained and proposed planting, open spaces and play areas;

c) The form of the development, with reference to densities, block types, building types, building heights, the palette of materials, recycling and waste management, street furniture, inclusive design;

d) The sequencing, hierarchy, typology and treatments of all elements of the movement network (including a proposed route to the eastern boundary to facilitate a highway link into Nightingale Wood within the appropriate Character Area Code);

e) Principles of traffic management, parking provision (including for the 5no. 'car share scheme parking spaces' across the site) and servicing to all properties;

f) The form of movement connections from within housing parcels to connect to the wider pedestrian/cycle network identified on 'Indicative Access and Movement Plan' (LHL005/162 rev P) that provide connectivity to facilities and services; and

g) Any alterations to public transport routes to accommodate the defined phases of development within the site.

Each reserved matters application shall be accompanied by a checklist to demonstrate where the development accords with the relevant approved Character Area Design Code.

Reason: To ensure a holistic approach to co-ordinate and deliver high quality design in accordance with Policy DE1 and Policy NC3 of the Swindon Borough Local Plan 2026.

Strategic highways infrastructure will be the first reserved matters applications on the site to allow construction access.  As the general design and location of the access points has been previously accepted by the Local Highways Authority, it is not considered that this needs to be covered by a Design Code.  The proposed amendments would retain the requirement for Design Codes to cover all other development parcels and it should be noted that the design parameters for the South Marston Main Street will already be picked up through the Strategic Design Code.  The revised wording sought does not materially affect the ability to secure Design Codes for development parcels and will positively support early delivery of important infrastructure (site accesses) and the wider delivery of the site.

CONDITION 27 – OLD VICARAGE LANE/A420

Proposed wording:

No work to commence on site that requires access from the OVL until an interim works scheme, in general accordance with drawing 1335-060-03 (submitted to LPA on 21st October 2019) and detailed design for the highway scheme improvement works to OVL junction with the A420, in general accordance with drawing 1335-HL-72-Rev C (submitted to LPA on 13th October 2017) have been submitted and approved in writing by the LPA and has been let to contract. The interim works shall be in place prior to the commencement of development, that requires access taken off the OVL, and the highway scheme improvement works to the junction must be complete to base course and operational before the first dwelling is occupied, where access is taken off the OVL.

Reason: To ensure a satisfactory junction facility is provided in a timely manner in the interests of highway safety and capacity in accordance with local pan policy TR1 and TR2.

The construction access for South Marston will be via Thornhill Road junction, having regard to evidenced challenges with routing large construction vehicles under the railway bridge where there are height restrictions.  The condition as drafted requires the interim works to be in place prior to commencement of development, however if development traffic (including as part of site preparation/construction) is not taken off the OVL, there is no need for any junction works to be in place.

As the intention is to use Thornhill Road junction as the construction access, and not the OVL, it is unlikely that the interim OVL/A420 scheme will not be constructed, and as such the full signalised works will be built out at an early stage, and prior to the first occupation where access is taken off the OVL, in accordance with the outline condition and ensuring that construction and residential traffic are kept separate.  The revised wording sought does not materially affect the ability to secure agreed mitigation and will positively support early delivery of important infrastructure (site accesses) and the wider delivery of the site.

CONDITION 41 – SURFACE WATER – FULL SITE

Proposed wording:

Development shall not begin (with the exception of S.278 access works) until a detailed Surface Water Management Strategy for the site, has been submitted to, and approved in writing by the Local Planning Authority. The strategy shall include:

a) Evidence that the proposed flows from the site will be restricted to 4.83l/s/ha for all events up to and including events up to and including the 1% AEP + climate change event (40%);

b) Details of how the drainage strategy has been designed to incorporate SuDS techniques to manage water quantity and maintain water quality as set out in the FRA and adopted policy and best practice guidance including the latest SuDS Manual C753;

c) Details of swales and other overland drainage features to manage the existing surface water flow routes through the site, as highlighted on Plan 1335-DR-05 Rev C (submitted to LPA on 16th July 2020);

d) Detailed drainage plan showing the location of the proposed SuDS and drainage network with exceedance flow routes clearly identified as highlighted on Plan 1335-DR-05 Rev C (submitted to LPA on 16th July 2020), that acknowledges the role of green infrastructure resource to accommodate additional features to augment the detailed design if required);

e) Details of how the strategy shall be maintained and managed after completion;

f) Details of how water quality shall be maintained during and after construction;

g) Detailed drainage calculations for all rainfall events up to and including the 1 in 100 year plus climate change event (40%) to demonstrate that all SuDS features and the drainage network can cater for the critical storm event for its lifetime;

h) The submission of evidence relating to accepted outfalls from the site, particularly from any third party network owners; and

i) Sequencing for implementation.

The scheme shall be implemented in accordance with the approved details and timetable.

Reason: To ensure the surface water management strategy (and future phases of development) will comply with the adopted policy and best guidance and that the development will not increase the risk of flooding elsewhere; in accordance with Paragraph 159 of the National Planning Policy Framework (NPPF) and Policy EN6 of the adopted Swindon Local Plan 2026.

This condition requires approval of the site wide drainage strategy for the development scheme, at an early stage in the site implementation, to guide subsequent phased/ detailed design and to ensure integration of a site wide approach to managing surface water.

The access junctions, that are pursuant to access conditions 26 (Thornhill Road) C 27 (OVL/A420) C 28 (Eastern Access) and C30 (OVL)  - also referred to as s278 works, will be designed as extensions to the existing highway, and as such the drainage design will connect into the existing drainage infrastructure within the local highway, and will not rely on new surface water management strategy for the site in order to drain the access junctions.

As the site wide SW drainage strategy is not required to deliver the access junctions, the revised wording does not materially affect the ability to secure agreed mitigation, and will positively support early delivery of important infrastructure (site accesses) and the wider delivery of the site.

CONDITION 47 – NOISE 1 RESIDENTIAL AMENITY

Proposed wording:

Prior to the commencement of any residential development within the areas shown green on plan 16/0492/SK7-1 a BS 4142:2014 (or later versions) assessment for that area, the scope of which has first been approved by the Local Planning Authority, shall be undertaken to determine the impact of commercial noise sources on the development hereby granted, and the findings submitted to and approved by the Local Planning Authority. Where the rating level of any noise source exceeds 5dB below the background level (LA90), as determined by the assessment, a scheme of mitigation to protect the amenity of the future occupants of the development shall be submitted to and approved by the Local Planning Authority. The agreed mitigation measures shall be implemented in accordance with the approved details and thereafter be permanently maintained.

Reason: To mitigate any harm arising from nearby noise sources and to ensure the development would provide an acceptable living environment for residents.

The condition as currently worded prevents any development on the areas in green on plan 16/0492/SK7-1a, including infrastructure, landscape, ecology, arboriculture and drainage works.  Clearly the intention of the condition is to protect residential amenity of occupiers, so the suggested wording will allow other development to take place as part of enabling the site, but retaining the intent of the condition which is to secure appropriate mitigation for residents.

CONDITION 49 – NOISE 3 – MECHANICAL VENTILATION

Proposed Wording:

Where the internal noise levels in bedrooms and living rooms specified in Noise Condition 2 will be exceeded with windows partially open by the dB ranges identified below, details of suitable ventilation systems shall be submitted to and approved in writing by the Local Planning Authority in accordance with the following ventilation systems as defined in Building Regulations Approved Document F (2010):

a) <-$5dB: ADF System 1, 2, 3 or 4

b) 5dB - 10dB: ADF System 3 (MEV) or 4 (MVHR)

c) <-$10dB: ADF System 4 (MVHR)

Reason: To ensure an acceptable living environment is provided for all occupiers of the development.

The condition currently has a formatting error, so the proposed revisions will clarify the original intended wording.

CONDITION 61 – BROADBAND

Proposed wording:

No residential nor mixed-use development shall take place within a sub-phase until details of measures to facilitate the availability of high speed broadband connection to the occupants within that sub-phase have been submitted to and approved in writing by the Local Planning Authority. The development shall be carried out in accordance with the approved details prior to the occupation of the buildings to which it relates.

Reason: To ensure access to appropriate broadband infrastructure in accordance with Policy IN3.

The wording of the condition would currently require broadband details for any works on site including the early reserved matters for strategic highway infrastructure which logically does not require a broadband connection.  The proposed revision will allow the early strategic highway infrastructure to take place without compromising the provision of broadband to future occupiers.

This application comprises:

- DLA Covering Letter

- Completed application form

- LHL005_144_G_Location Plan

- Planning Application Fee (£234)

The application has been submitted via the Planning Portal and we look forward to receiving confirmation of its validation as soon as possible.

We hope that this information is satisfactory but if you have any questions or concerns before determination, please do not hesitate to contact me so that these issues may be resolved to ensure that the application can be progressed and approved without delay.

Should you have any queries please do not hesitate myself or Sam Wood.

Yours sincerely,

Tanya Cosford

Associate Planner

Email:	tcosford@davidlock.com

cc:	fparmenter@davidlock.com

swood@davidlock.com